## Sheet1 (hidden)
PROJECT CLOSURE AND ACCEPTANCE |  |  |  |  | PC TECH – PLDT P3 Led Indoor Project
PROJECT NAME | PC TECH – PLDT P3 Led Indoor Project - SM City Clark
CLIENT |  | PMO | PROJECT START DATE | PROJECT END DATE
PC TECH |  | Francis Angulo | July 5, 2022 | July 9, 2022
DELIVERABLES
ITEM DESCRIPTION |  | PLANNED | ACTUAL | COMMENTS
1. Absen K3 Plus Panel(500x1000) |  | 2022-07-05 | 2022-07-05
2. Main Power Cable 5m w/ terminal |  | 2022-07-05 | 2022-07-05
3. Main Signal Cable / Belden Cat5e 305m | 3. Main Signal Cable / Belden Cat5e 305m | 2022-07-05 | 2022-07-05
4. Shielded RJ45 Connectors | 4. Shielded RJ45 Connectors | 2022-07-05 | 2022-07-05
5. Power Patch Cable | 5. Power Patch Cable | 2022-07-05 | 2022-07-05
6. Signal Patch Cable (U/D) | 6. Signal Patch Cable (U/D) | 2022-07-05 | 2022-07-05
7. Signal Patch Cable (L/R) | 7. Signal Patch Cable (L/R) | 2022-07-05 | 2022-07-05
8. Connecting Plates | 8. Connecting Plates | 2022-07-05 | 2022-07-05
9. Bolts, Nuts & Washers | 9. Bolts, Nuts & Washers | 2022-07-05 | 2022-07-05
10. Sending Box MCTRL300 w/ | 10. Sending Box MCTRL300 w/ | 2022-07-05 | 2022-07-05
accessories,Box,USB,DVI cable, P.cord | accessories,Box,USB,DVI cable, P.cord | 2022-07-05 | 2022-07-05
11. Omni Power strip 6 Gang Universal Outlet | 11. Omni Power strip 6 Gang Universal Outlet | 2022-07-05 | 2022-07-05
12. HDMI/DVI Cable 1m | 12. HDMI/DVI Cable 1m | 2022-07-05 | 2022-07-05
13. AVR Powerex 5Kva - Standard S.Phase | 13. AVR Powerex 5Kva - Standard S.Phase | 2022-07-05 | 2022-07-05
14. Cable Tie Black - 300x4x1.5mm /100s | 14. Cable Tie Black - 300x4x1.5mm /100s | 2022-07-05 | 2022-07-05
15. LED Software,Manual, 16Gb USB | 15. LED Software,Manual, 16Gb USB | 2022-07-05 | 2022-07-05
16. Module (spare) | 16. Module | 2022-07-05 | 2022-07-05
17. Scannning Cards w/ hub (spare) | 17. Scannning Cards w/ hub | 2022-07-05 | 2022-07-05
18. Power Supply (spare) | 18. Power Supply | 2022-07-05 | 2022-07-05
SCHEDULE
KEY MILESTONE |  | INITIAL DEADLINE | ACTUAL COMPLETION | COMMENTS
Installation of Steel Structures |  | 2022-07-05 | 2022-07-06
Stacking of LED |  | 2022-07-06 | 2022-07-06
Power and Data Cabling |  | 2022-07-06 | 2022-07-06
Cladding |  | 2022-07-09 | 2022-07-09
Power Up of LED |  | 2022-07-09 | 2022-07-19
Training |  | 2022-07-09
REMARKS / RECOMMENDATIONS
This is to certify that AVOLUTION INC. has successfully completed the entire requirements for "Supply, Delivery, and Installation of Absen K3 Plus Panel 3m x 2m for Smart/Sun Store located at SM City Clark, Angeles, Pampanga".
ISSUED BY:
NAME |  | COMPANY/POSITION | SIGNATURE | DATE
FRANCIS T. ANGULO |  | AVOLUTION INC / PMO
ACKNOWLEDGE BY:
NAME |  | COMPANY/POSITION | SIGNATURE | DATE

## Sheet1 (2)
CERTIFICATE OF ACCEPTANCE
This is to certify that AVOLUTION INC. has successfully completed the the entire requirements for "Supply, Delivery, and Installation of Absen K3 Plus(2mx2m) Indoor LED Display for PLDT-Smart One Digital Store SM City Tuguegarao", in accordance of with the approved specifications under the following contract; THIS IS A SAMPLE ONLY
| Contractor: |  | : | <CONTRACTOR NAME>
| Contract Package and Description |  | : | <DESCRIPTION>
| Date of Delivery |  | : | <DATE>
| Date of Completion |  | : | <DATE>
Issued by:
Accepted by:
Signature over printed name
Position
Date
LED BILLBOARD DISPLAY | DIGITAL DISPLAYS
DIGITAL EVENT SOLUTIONS | CONTENT CREATION & MANAGEMENT LED MAINTENANCE AND REPAIR | LED ADVERTISING PLACEMENT